## Reconciliation Matrix
Seagull Maritime — Reconciliation Matrix
SM/INT/REG/005 v1.0 ¦ Cross-reference of all tracked items across registers and programmes
Item Ref | Description | Source | Overall Status | NCR Register (REG/004) | CWP (CMP/002) | IA-001 CMP (Doc Control) | IA-002 CMP (Risk Mgmt) | Owner | Target Date | Notes
Shell F1 / NCR-001 | Malta exemption documentation — license to operate | Shell Audit | In Progress | NCR-001 In Progress | 1.11 Ongoing 1.05 Completed (legal infrastructure) | — | — | Legal | Ongoing | Awaiting Malta response
Shell F2 / NCR-002 | Risk management system — ISO 45001 + unified framework | Shell Audit | In Progress | NCR-002 CA In Progress — substantial evidence | 1.01-1.04 Completed 2.01 Completed 2.17 Completed 1.05 Completed 2.10 Completed 2.08 In Progress 3.02 In Progress 2.09 Completed 2.14 Completed | — | CMP-001 In Progress CMP-004 Completed CMP-005 In Progress CMP-007 Completed | D. Watts | 14/04/2026 | S16: 8 H&S RAs completed. S19: Legal infrastructure built. S26-S28: WAF DD complete — SM/OPS/SOP/002 (WAF SOP), SM/SEC/DOC/002 (WAF OCIMF Checklist), SM/SEC/PRO/002 v1.1 (DD Procedure IOR+WAF), DD portals live (IOR+WAF+CSM). LMS live with mandatory courses. Training rollout + 45001 cert still required. Updated 04/04/2026. S34: PRO-017 (procurement), PRO-019 (MR), FORM/004-006, REG-010, SEV forms corrected. 45001 Cl. 6.1.4/8.1.4/9.1/9.3/10.1 all Completed. Updated 08/04/2026.
Shell F3 / NCR-008 | Media & social media policy | Shell Audit | In Progress | NCR-008 In Progress | 1.07 In Progress | — | — | D. Watts | Closed | Draft exists. Needs new template format rebuild and formal release. Training pending.
Shell F4 / NCR-009 | Insurance entity alignment (UK vs Malta) | Shell Audit | Closed | NCR-009 Closed | 1.12 Completed | — | — | Legal | Closed | Documentation aligned and filed.
Shell F5 / NCR-010 | Nigerian Navy MOU | Shell Audit | Closed | NCR-010 Closed | F5 Completed | — | — | CEO / WAF Ops | Closed | MOU received. Training review pending.
Shell F6 / NCR-003 | VPSHR integration into procedures/training | Shell Audit | In Progress | NCR-003 CA Implemented | 1.04 Completed 2.08 In Progress 3.02 In Progress | — | — | D. Watts | 16/03/2026 | S14: OH&S Policy VPSHR. S21: IOR SOPs. S22: RUF. S24: Code of Conduct. S25: Training courses. S26: WAF SOPs + SEV procedures (VPSHR scope). S28: LMS — SEV course live, WAF ops mandatory. Training rollout in progress. Updated 04/04/2026.
Shell F7 / NCR-004 | IRT exercise documentation | Shell Audit | Completed | NCR-004 CA Implemented. SM/HSE/RPT/001 completed. | 3.06 Completed (08/04/2026) | — | — | D. Watts | 27/02/2026 | IRT exercise completed 27/03/2026 (tabletop, Piraeus office fire). Report: SM/HSE/RPT/001. 4 OFIs raised (OFI-013 to OFI-016).
Shell OFI1 / OFI-001 | Management of Change process | Shell Audit | Completed | OFI-001 CA Implemented | 1.06 Completed | — | CMP-002 Completed | D. Watts | 14/04/2026 | SM/INT/PRO/013 v1.0 + SM/INT/FORM/003 + SM/INT/REG/009. Full MoC suite. Supersedes SM/PRO/CHA/001. S33.
Shell OFI2 / OFI-002 | Management review cycle | Shell Audit | Completed | OFI-002 Completed | 2.14 Completed, 3.07 Completed | — | — | D. Watts | 15/03/2026 | S34: PRO-019 Management Review Procedure v1.0 built. MRM-001 v1.1 updated. Full close-out. 08/04/2026.
Shell OFI3 / OFI-003 | Sanctions listings — embed US checks | Shell Audit | In Progress | OFI-003 In Progress | 1.10 Pending | — | — | D. Watts | 25/02/2026
Shell OFI4 / OFI-010 | Vessel delay wording | Shell Audit | Completed | OFI-010 Completed | 2.11 Completed | — | — | D. Watts | Completed | SOP annex amended. Formal reissue pending.
Shell OFI5 / OFI-011 | UKMTO incident reporting | Shell Audit | Completed | OFI-011 Completed | 2.12 Completed | — | — | D. Watts | Completed | SOP annex amended. Formal reissue pending.
Shell OFI6 / OFI-004 | SEV minimum standards | Shell Audit | CA Implemented | OFI-004 CA Implemented | 2.10 Completed / OFI6 Completed | — | — | C. Antzoulatos | 01/03/2026 | S28: PRO-004 (27 vessel standards), PRO-005 (11 provider standards), FORM-001 (SEV Checklist), FORM-002 (WAF DD Checklist), DOC-002 (WAF OCIMF Checklist — 52 questions). PRO-002 v1.1 DD procedure covers IOR + WAF. DD portals live. WAF team rollout pending. Updated 04/04/2026.
Shell OFI7 / OFI-005 | D&A Policy applicability | Shell Audit | In Progress | OFI-005 In Progress | 1.08 Pending | — | — | Legal / D. Watts | 01/03/2026 | Legal reviewing.
Shell OFI8 / OFI-012 | PCASP briefing to Masters | Shell Audit | Completed | OFI-012 Completed | 3.05 Pending | — | — | D. Watts | Completed | Briefing finalised. Formal distribution pending.
IA-002 F1 / NCR-005 | R&O Register outdated and incomplete | IA-26-002 | Open | NCR-005 Open | — | — | CMP-003 Open | D. Watts | 21/04/2026 | S14: COTO (SM/INT/DOC/002) PESTLE/SWOT completed — feeds risk register rebuild. Corporate register rebuild still required.
IA-002 F3 / NCR-006 | MoC procedure inadequate (MSP-B-09) | IA-26-002 | Open | NCR-006 Open | 1.06 Pending | — | CMP-002 Open | D. Watts | 14/04/2026 | Full rebuild from template. Also Shell OFI1.
IA-002 F4 / NCR-007 | Legal Requirements Register inadequate | IA-26-002 | Completed | NCR-007 — CA Implemented | 1.05 Completed | — | CMP-004 Completed 01/04/2026 | D. Watts | 21/04/2026 | Monday.com interim still in use.
IA-002 F5 / OFI-006 | Risk architecture documentation | IA-26-002 | In Progress | OFI-006 In Progress | — | — | CMP-005 In Progress | D. Watts | 14/04/2026 | S16: Risk assessment architecture now fully built (RA-003 pattern, 8 RAs, dashboards, methodology). S19: Night Operations RA added (9th RA, 144 total hazards). Architecture documented in SM/HSE/PRO/001 and SM/SEC/PRO/001.
IA-002 F6 / OFI-007 | Modernise Risk Policy | IA-26-002 | In Progress | OFI-007 In Progress (tracked changes applied S24) | — | — | CMP-006 In Progress | D. Watts | 05/05/2026 | Depends on risk procedure.
IA-002 F8 / OFI-008 | Withdraw legacy MSP risk docs | IA-26-002 | In Progress | OFI-008 In Progress | — | — | CMP-008 In Progress | D. Watts / E. Lukshin | 28/04/2026 | Option A migration partially addresses this.
IA-002 F9 / OFI-009 | Risk management awareness programme | IA-26-002 | Open | OFI-009 Open | 3.02/3.03 Pending | — | CMP-009 Open | D. Watts / O. Yurasov | 05/05/2026 | Phase 3 training. SM/INT/PRO/010 provides framework. SM/TRG/DOC/001-002 (HR training) built. SM/INT/REG/008 (competence matrix) complete. Emergent LMS live: AI quizzes, certificates, leaderboard, mandatory courses, Operations-IOR/WAF role split. Updated 04/04/2026.
IA-001 F1 | Populate Document Register | IA-26-001 | Completed | — | — | CMP-001 Completed | — | D. Watts | Completed | SM/INT/REG/001 v2.0 — 26 documents.
IA-001 F2 | Migrate Control of Documents procedure | IA-26-001 | Completed | — | 1.09 Completed | CMP-002 Completed | — | D. Watts | Completed | SM/INT/PRO/002 issued. Option A.
IA-001 F4 | Single document control hierarchy | IA-26-001 | Completed | — | — | CMP-004 Completed | — | D. Watts | Completed | Option A migration. Old refs withdrawn.
IA-001 F6 | Document referencing convention | IA-26-001 | Completed | — | — | CMP-006 Completed | — | D. Watts | Completed | SM/INT/DOC/001 issued. COTO renumbered to SM/INT/DOC/002 (S14).
IA-001 F8 | External docs register | IA-26-001 | Completed | — | — | CMP-008 Completed | — | D. Watts | Completed | SM/INT/REG/007 External Standards and References Register v1.0 — 27 entries, 8 categories. Completed 01/04/2026 (S19). Was showing Pending — corrected S28.
45001 Cl. 4.1 | Context of the Organisation (PESTLE & SWOT) | ISO 45001 | Completed | — | 1.02 Completed | — | — | D. Watts | Completed | SM/INT/DOC/002 v1.0 (pre-war) + v2.0 (Iran emergency review). INT prefix — cross-cutting.
45001 Cl. 4.2 | Interested Parties Register | ISO 45001 | Completed | — | 1.03 Completed | — | — | D. Watts | Completed | SM/HSE/REG/001 v1.0. 21 parties, Power/Interest Matrix. Iran conflict in review notes.
45001 Cl. 4.3 | OH&S Management System Scope Statement | ISO 45001 | Completed | — | 1.01 Completed | — | — | D. Watts | Completed | SM/HSE/DOC/001 v1.0. Sent to Libero. All entities, locations, activities covered.
45001 Cl. 5.2 | OH&S Policy | ISO 45001 | Completed | — | 1.04 Completed | — | — | D. Watts | Completed | SM/HSE/POL/001 v1.0. Cl. 5.2 mandatory + Seagull-specific commitments. CEO sign-off pending.
45001 Cl. 6.1.2 | Hazard identification and assessment of risks and opportunities | ISO 45001 | Completed | — | 2.01/2.17 | — | CMP-001 In Progress | D. Watts | Completed | SM/HSE/RA/002-009 (8 RAs, 130 hazards). SM/CAM/BRAG/001-008 (8 BRAGs for frontline). RA-003 gold standard pattern established. Completed 31/03/2026. 6.1.1 also completed — SM/HSE/PRO/001 issued 31/03/2026.
45001 Cl. 6.1.1 | Actions to address risks and opportunities — General | ISO 45001 | Completed | — | 2.01 Completed | — | — | D. Watts | Completed | SM/HSE/PRO/001 Hazard ID & Risk Assessment Procedure v1.0 issued 31/03/2026. Defines framework for all RA-003 and RA-004 pattern assessments.
45001 Cl. 6.2 | OH&S objectives and planning to achieve them | ISO 45001 | Completed | — | 2.02 Completed | — | — | D. Watts | Completed | SM/INT/REG/006 Company Objectives Register v1.0. 30 SMART objectives across HSE (7), SEC (7), QMS (3), INT (13). Dashboard, review history, data validation. Completed 31/03/2026.
45001 Cl. 6.1.3 | Determination of legal requirements and other requirements | 45001 Clause | Completed | NCR-007 — CA Implemented | 1.05 Completed 3.10 Pending (compliance assessment) | — | CMP-004 Completed | D. Watts
IA-001 CMP-008 | Populate external documents register | IA-26-001 | Completed | — | 1.05 Completed | CMP-008 Completed 01/04/2026 | — | D. Watts
DD Process | SM/SEC/PRO/002 v1.1 + SM/SEC/DOC/001 (IOR) + SM/SEC/DOC/002 (WAF) | Due diligence response procedure + OCIMF checklists (IOR + WAF) | Completed | SM/INT/REG/001 | Completed | 04/04/2026 |  |  |  | S20: IOR DD built. S28: WAF OCIMF Checklist (52 Qs, Word format), PRO-002 v1.1 (IOR+WAF), DD portals live (IOR+WAF+CSM). PG removed. Updated 04/04/2026.
45001 Cl. 7.5 | Documented information — control of records | ISO 45001 | Completed | — | 7.5 Completed | CMP-005 Completed CMP-006 Completed | —
45001 Cl. 7.2/7.3 | Competence and Awareness | ISO 45001 | In Progress | — | 3.01 Completed 3.02 In Progress 3.09 Completed | — | — | D. Watts | 21/04/2026 | SM/INT/PRO/010 approved. SM/INT/REG/008 (20 courses × 41 personnel). SM/TRG/DOC/001-002 (HR training courses). Emergent LMS live: mandatory courses matrix, certificate sharing, Operations-IOR/WAF role split, SEV course live. Training rollout in progress. Updated 04/04/2026.
45001 Cl. 5.3 | Organisational roles, responsibilities and authorities | ISO 45001 | Completed | — | 2.03 Completed | — | — | D. Watts | Completed | SM/INT/DOC/005 RACI Matrix v1.0. 48 functions, 11 roles, 7 categories. S34 — 8 Apr 2026.
45001 Cl. 5.4 | Consultation and participation of workers | ISO 45001 | Completed | — | 2.04 Completed | — | — | D. Watts | Completed | SM/INT/PRO/014 Worker Consultation and Participation Procedure v1.0. S34 — 8 Apr 2026.
45001 Cl. 8.2 | Emergency preparedness and response | ISO 45001 / Shell F7 | Completed | — | 2.05 Completed 3.06 Pending (IRT) | — | — | D. Watts | Completed (doc) IRT May 2026 | SM/HSE/PRO/003 v1.0. Umbrella procedure. IRT exercise target before May 2026. S34.
45001 Cl. 10.3 | Continual improvement | ISO 45001 | Completed | — | 2.18 Completed | — | — | D. Watts | Completed | SM/INT/PRO/015 Continual Improvement Procedure v1.0. S34 — 8 Apr 2026.

## Instructions
RECONCILIATION MATRIX — INSTRUCTIONS
Purpose
This matrix provides a single-view cross-reference of every tracked finding, NCR, OFI, and action across all Seagull Maritime registers and programmes. It answers the question: "Where is this tracked, and what's the status everywhere?"
When to update
Every time a deliverable is completed that relates to a tracked item. Update the matrix AND the source registers simultaneously (Option 2 discipline).
Column guide
Item Ref = primary identifier across registers. NCR Register / CWP / IA CMPs = status in each tracker. Overall Status = worst-case across all trackers (an item is only Completed when ALL related tasks are done everywhere).
Colour coding
Green = Completed/Closed. Blue = In Progress/Ongoing. Yellow = Open/Pending. Dash = not tracked in that register.
Adding new items
When a new finding or OFI is raised, add a row to this matrix AND the NCR register. Cross-reference to any programme tasks it relates to.
Review cycle
Review this matrix at the start of every session and before any Shell/auditor engagement. It is the fastest way to understand overall compliance posture.