## Objectives
Company Objectives Register
Seagull Maritime Ltd ¦ SM/INT/REG/006 ¦ Last Review: March 2026 ¦ Next Review: September 2026
Ref | ISO System | ISO Clause | Business Function | Objective | SMART Description | KPIs | Owner | Supporting | Target Date | Status | RAG | Progress % | Evidence | MR Action Ref
OBJ-001 | HSE | 6.2 / 45001 | Compliance | Achieve ISO 45001:2018 initial certification | Obtain initial ISO 45001:2018 certification from Libero Assurance by Q2 2026. Pass Stage 1 and Stage 2 audits with no major non-conformities. Build 3 months implementation evidence. | Stage 1 passed; Stage 2 passed; Certificate issued; Zero major NCs | D. Watts (GCD) | Pavel Shparber (CEO) | 2026-06-30 | On Track | Amber | 55 | SM/HSE/POL/001; SM/HSE/PRO/001; SM/HSE/RA/002-009; SM/HSE/DOC/001; SM/INT/DOC/002; CWP | MRM-2026-A1
OBJ-002 | HSE | 6.2 / 45001 | Operations | Zero serious workplace injuries across all operations | Achieve and maintain zero lost-time injuries (LTIs) and zero serious workplace incidents across all operational theatres (IOR, PG, WAF) and office environments throughout 2026. | LTI count = 0; RIDDOR reportable = 0; Near-miss rate ≥2/vessel/month | D. Watts (GCD) | Operations Managers | 2026-12-31 | On Track | Green | 25 | Emergent HSE App incident data; Vessel logs | MRM-2026-A2
OBJ-003 | HSE | 6.2 / 45001 | Operations | Establish proactive near-miss and hazard reporting culture | Implement company-wide near-miss and hazard reporting via the Emergent HSE App. Target minimum 2 reports per vessel per month. Track trends quarterly. | Reports per vessel ≥2/month; Quarterly trend analysis; App adoption 100% | D. Watts (GCD) | Oleksii Yurasov | 2026-09-30 | On Track | Green | 30 | Emergent HSE App data; Quarterly HSE reports | MRM-2026-A3
OBJ-004 | HSE | 6.2 / 45001 | Compliance | Complete H&S risk assessments for all operational activities | Develop and maintain comprehensive H&S risk assessments (RA-003 pattern) covering all operational, office, and remote working activities. Minimum 100 hazards assessed with controls. | RAs completed; Total hazards ≥100; All RAs reviewed within 12 months | D. Watts (GCD) | Operations Managers | 2026-03-31 | Completed | Green | 100 | SM/HSE/RA/002-009 (8 RAs, 130 hazards); SM/CAM/BRAG/001-008 | MRM-2026-A4
OBJ-005 | HSE | 6.2 / 45001 | Operations | Deliver H&S awareness training to all operational personnel | Ensure 100% of operational personnel complete H&S awareness training via the company's online training platform by Q3 2026. Include vessel transfer, weapons handling, heat stress modules. | Training completion ≥95%; Module pass rate ≥80%; Overdue count = 0 | Oleksii Yurasov | D. Watts (GCD) | 2026-09-30 | Not Started | Amber | 5 | Training platform data; Training Register | MRM-2026-A5
OBJ-006 | HSE | 6.2 / 45001 | Operations | Implement heat stress management for Gulf operations | Establish and enforce heat stress management protocols for all Persian Gulf operations. Issue BRAG guidance, monitor WBGT readings, ensure all PG personnel briefed. | BRAG distributed 100% PG teams; WBGT monitoring in place; Zero heat incidents | D. Watts (GCD) | PG Operations Manager | 2026-06-30 | On Track | Green | 40 | SM/HSE/RA/009; SM/CAM/BRAG/008 | MRM-2026-A6
OBJ-007 | HSE | 6.2 / 45001 | Compliance | Distribute BRAGs to 100% of frontline teams | Ensure all 8 BRAGs are distributed to every operational team across IOR, PG, and WAF. Physical copies on every vessel, digital copies via campaign portal. | Distribution per vessel confirmed; Portal access logged; Acknowledgement ≥90% | D. Watts (GCD) | Operations Managers | 2026-06-30 | In Progress | Green | 20 | SM/CAM/BRAG/001-008; Distribution records; Campaign portal | MRM-2026-A7
OBJ-008 | SEC | 6.2 / 18788 | Compliance | Maintain ISO 18788:2015 certification | Pass 2026 surveillance audit and maintain ISO 18788:2015 certification with no major non-conformities. | Audit outcome; NC count = 0 major; CAR closure 100% | D. Watts (GCD) | Pavel Shparber (CEO) | 2026-12-31 | On Track | Green | 25 | Audit reports; Internal audit programme; NCR Register | MRM-2026-B1
OBJ-009 | SEC | 6.2 / 28007 | Compliance | Maintain ISO 28007:2015 certification | Pass 2026 surveillance audit and maintain ISO/PAS 28007:2015 certification with no major non-conformities. | Audit outcome; NC count = 0 major; CAR closure 100% | D. Watts (GCD) | Pavel Shparber (CEO) | 2026-12-31 | On Track | Green | 25 | Audit reports; Internal audit programme; NCR Register | MRM-2026-B2
OBJ-010 | SEC | 6.2 / 28000 | Compliance | Maintain ISO 28000:2022 certification | Pass 2026 surveillance audit and maintain ISO 28000:2022 certification with no major non-conformities. | Audit outcome; NC count = 0 major; CAR closure 100% | D. Watts (GCD) | Pavel Shparber (CEO) | 2026-12-31 | On Track | Green | 25 | Audit reports; Internal audit programme; NCR Register | MRM-2026-B3
OBJ-011 | SEC | 6.2 / 18788 | Operations | Zero security incidents attributable to procedural failures | Achieve zero security-related incidents attributable to failures in procedure, training, or risk management across all operational theatres throughout 2026. | Incident count from procedure failure = 0; Root cause analysis for all incidents | D. Watts (GCD) | Operations Managers | 2026-12-31 | On Track | Green | 25 | Incident reports; After-action reviews; NCR Register | MRM-2026-B4
OBJ-012 | SEC | 6.2 / 18788 | Compliance | Complete security risk assessments for all theatres (RA-004) | Develop security and business risk assessments (RA-004 PESTLE pattern) for all active operational theatres: IOR, PG, and WAF. | RAs per theatre completed; All theatres covered; Quarterly review cycle | D. Watts (GCD) | Operations Managers | 2026-06-30 | In Progress | Green | 33 | SM/SEC/RA/001 (IOR); RA-004 pattern RAs for PG and WAF pending | MRM-2026-B5
OBJ-013 | SEC | 6.2 / 18788 | Compliance | Integrate VPSHR into all operational procedures and training | Ensure VPSHR are explicitly referenced and integrated into all operational SOPs, security procedures, and training materials. | VPSHR in 100% operational SOPs; Training module developed; Awareness ≥90% | D. Watts (GCD) | Oleksii Yurasov | 2026-09-30 | In Progress | Amber | 15 | Shell F6 (NCR-006); Operational SOPs; Training records | MRM-2026-B6
OBJ-014 | SEC | 6.2 / 28007 | Compliance | Maintain 100% flag state authorisation compliance | Ensure all flag state authorisations are current, valid, and renewed before expiry for every flag state. | Zero expired authorisations; Renewal tracker current; 30-day advance trigger | D. Watts (GCD) | Olga Zuck (CCO) | 2026-12-31 | On Track | Green | 50 | Flag state register; Renewal correspondence | MRM-2026-B7
OBJ-015 | QMS | 6.2 / 9001 | Compliance | Maintain ISO 9001:2015 certification | Pass 2026 surveillance audit and maintain ISO 9001:2015 certification with no major non-conformities. | Audit outcome; NC count = 0 major; CAR closure 100% | D. Watts (GCD) | Pavel Shparber (CEO) | 2026-12-31 | On Track | Green | 25 | Audit reports; Internal audit programme; NCR Register | MRM-2026-C1
OBJ-016 | QMS | 6.2 / 9001 | Commercial | Establish structured client feedback mechanism | Implement formal client satisfaction monitoring with regular feedback collection, trend analysis, and quarterly reporting to management review. | Mechanism deployed; Quarterly reports produced; Response rate ≥50% | Olga Zuck (CCO) | D. Watts (GCD) | 2026-09-30 | Not Started | Amber | 0 | Client feedback forms; Quarterly satisfaction reports | MRM-2026-C2
OBJ-017 | QMS | 6.2 / 9001 | Commercial | Achieve client satisfaction rating above 90% | Achieve and maintain client satisfaction above 90% across all service lines, measured from structured feedback per contract. | Average score ≥90%; Individual contract ≥80%; Quarterly trend analysis | Olga Zuck (CCO) | Christoforos Antzoulatos | 2026-12-31 | Not Started | Grey | 0 | Client satisfaction register (dependent on OBJ-016) | MRM-2026-C3
OBJ-018 | INT | 6.2 / Multi | Compliance | Unify management system across all ISO standards | Complete integration of 45001 into existing security and quality management system. Single document structure, common procedures, unified audit programme. | Unified document register; Cross-standard procedures; Single audit programme | D. Watts (GCD) | Pavel Shparber (CEO) | 2026-06-30 | On Track | Green | 45 | SM/INT/CMP/002 (CWP); Document Register; Internal Audit Schedule | MRM-2026-D1
OBJ-019 | INT | 6.2 / Multi | Compliance | Close all Shell audit findings before May review | Close or demonstrate substantial progress on all 7 Shell findings and 8 OFIs before the Shell review first week of May 2026. | Findings closed: 7/7; OFIs closed: 8/8; Evidence per finding | D. Watts (GCD) | Pavel Shparber (CEO) | 2026-05-09 | On Track | Amber | 50 | NCR Register (SM/INT/REG/004); Shell CMP; Evidence folders | MRM-2026-D2
OBJ-020 | INT | 6.2 / Multi | Compliance | Deliver 2026 internal audit programme | Complete all scheduled internal audits covering all ISO clause areas across 45001, 18788, 28007, 28000, and 9001. | Audits completed vs scheduled; Coverage map; All findings tracked | D. Watts (GCD) | Future QHSE Manager | 2026-12-31 | In Progress | Green | 20 | SM/INT/REG/003 (Audit Schedule); Audit reports | MRM-2026-D3
OBJ-021 | INT | 6.2 / Multi | Compliance | Establish biannual management review cycle | Conduct management reviews every 6 months covering all ISO inputs per Clause 9.3. Next review due September 2026. | MR meetings vs scheduled; Action closure ≥90%; Minutes within 5 days | D. Watts (GCD) | Pavel Shparber (CEO) | 2026-09-30 | On Track | Green | 50 | SM/INT/MRM/001; Management Review Minutes | MRM-2026-D4
OBJ-022 | INT | 6.2 / Multi | Compliance | Deploy compliance awareness campaign company-wide | Launch and sustain 'Your Watch. Our Standard.' campaign. Quarterly bulletins, flash cards, BRAGs distributed to all teams. | Bulletins ≥4/year; Flash cards per topic; BRAG distribution 100%; Portal engagement | D. Watts (GCD) | Operations Managers | 2026-12-31 | On Track | Green | 25 | SM/CAM/BUL/001; SM/CAM/FC/001; Campaign portal | MRM-2026-D5
OBJ-023 | INT | 6.2 / 7.2 | Compliance | Implement integrated training platform | Deploy the company's online training platform with AI-powered quiz generation, certificates, and progress tracking for all ISO-required training. | Platform live; Courses published; Completion tracking active; Certificates working | D. Watts (GCD) | Oleksii Yurasov | 2026-06-30 | In Progress | Green | 40 | Training platform (preview); Course catalogue; Training Register | MRM-2026-D6
OBJ-024 | INT | 6.2 / 7.5 | Compliance | Complete management system document migration | Migrate all legacy documents to SM/ referencing format with standardised formatting, version control, and Document Register tracking. | Documents migrated %; Register entries vs baseline; Zero unreferenced active docs | D. Watts (GCD) | Eugene Lukshin | 2026-09-30 | In Progress | Amber | 35 | Document Register (SM/INT/REG/001); Legacy Mapping | MRM-2026-D7
OBJ-025 | INT | 6.2 / Multi | Compliance | Build and maintain Due Diligence portal | Maintain client-facing DD portal with current documentation. Update within 5 working days of changes. Migrate to portals.seagullmaritimeltd.com. | Uptime 99%; Currency ≤5 days; Client access logs; Subdomain live | D. Watts (GCD) | Eugene Lukshin | 2026-12-31 | On Track | Green | 60 | DD Portal (GitHub Pages); 107 documents hosted | MRM-2026-D8
OBJ-026 | INT | 6.2 / 7.2 | HR | Recruit dedicated QHSE Manager | Recruit a QHSE Manager to support the GCD and ensure ongoing management system maintenance and development. | Recruitment status; Start date; Induction completion; Handover of routine tasks | Pavel Shparber (CEO) | D. Watts (GCD) | 2026-09-30 | Not Started | Amber | 0 | SM/INT/JD/003 (QHSE Manager JD); Recruitment records | MRM-2026-D9
OBJ-027 | INT | 6.2 / Multi | Operations | Complete IRT exercise and documentation | Plan, execute, and document a formal Incident Response Team exercise covering security incident scenarios. | Exercise planned; Completed; After-action report issued; Lessons actioned | D. Watts (GCD) | Operations Managers | 2026-06-30 | Not Started | Amber | 0 | Shell F7 (NCR-007); Exercise plan; After-action report | MRM-2026-D10
OBJ-028 | INT | 6.2 / Multi | Compliance | Resolve Malta exemption documentation (Shell F1) | Obtain and file Maltese exemption documentation (S.L. 480.05 / Arms Act) for PMSC operations under Malta flag. | Documentation received; Filed; Shell F1 closed | D. Watts (GCD) | Olga Zuck (CCO) | 2026-06-30 | On Track | Amber | 30 | Shell F1 (NCR-001); Malta correspondence | MRM-2026-D11
OBJ-029 | INT | 6.2 / Multi | Operations | Establish SEV minimum standards | Develop and implement minimum operational standards for Security Escort Vessels covering crew competency, equipment, maintenance, and readiness. | Standards published; All SEVs assessed; Gap closure plan per vessel | D. Watts (GCD) | Christoforos Antzoulatos | 2026-09-30 | Not Started | Amber | 0 | Shell OFI-006; SEV standards document | MRM-2026-D12
OBJ-030 | INT | 6.2 / Multi | Compliance | Implement Management of Change process | Develop and deploy formal MoC procedure covering operational, organisational, and system changes with risk assessment and approval workflows. | MoC procedure published; Register established; All changes tracked; Zero uncontrolled | D. Watts (GCD) | Pavel Shparber (CEO) | 2026-09-30 | Not Started | Amber | 0 | Shell OFI-001; MoC procedure; MoC register | MRM-2026-D13
OBJ-031 | INT | 6.2 / 7.2 | Compliance | Develop Eugene Lukshin into effective compliance support role | Implement structured development plan for Eugene covering document control, register maintenance, training administration, and basic audit support. Monthly progress reviews against competency milestones. | Development plan published; Monthly reviews completed; Milestones achieved; Independent task rate | D. Watts (GCD) | Eugene Lukshin | 2026-09-30 | Not Started | Amber | 5 | SM/INT/JD/002 (Compliance Admin JD); Development plan; Review notes | MRM-2026-D14
OBJ-032 | INT | 6.2 / 7.2 | HR | Review and formalise shore-side staff HR and training processes | Review and formalise HR processes and training records for shore-side personnel, currently managed through PSS. Ensure management system captures competence, training evidence, and personnel records. | HR process review completed; Training records current 100% shore-side; Gap analysis done | D. Watts (GCD) | Oleksii Yurasov | 2026-09-30 | Not Started | Amber | 0 | Training Register; HR process documentation; PSS staff records | MRM-2026-D15

## Dashboard
Objectives Dashboard
Auto-calculated summary from Objectives sheet
By ISO System |  | By Status
System | Count | Status | Count
HSE | 7 | On Track | 16
SEC | 7 | Completed | 1
QMS | 3 | In Progress | 6
INT | 15 | Not Started | 9
TOTAL | 32 | At Risk | 0
|  | Overdue | 0
By RAG |  | Progress Statistics
RAG | Count | Metric | Value
Green | 18 | Average Progress | 26.8125
Amber | 13 | Maximum Progress | 100
Red | 0 | Minimum Progress | 0
Grey | 1 | Total Objectives | 32

## Review History
Objectives Review History
Record of reviews for Clause 9.1 monitoring evidence
Review Date | Review Period | Reviewer | Summary | Actions Arising | Next Review Due
31/03/2026 | Q1 2026 (Jan-Mar) | D. Watts (GCD) | Initial register established with 32 objectives across HSE (7), SEC (7), QMS (3), and Integrated (15). All 18 management review objectives mapped and expanded. 1 completed (H&S RAs). 12 on track, 6 in progress, 8 not started. Strong momentum from S15-S16. | 1. Prioritise 45001 documentation for May Shell review. 2. Begin H&S training module development. 3. VPSHR integration into SOPs. 4. Recruit QHSE Manager (CEO action). 5. Deploy training platform to production. | 30/06/2026

## Lists
Status | RAG | ISO System | Business Function | ISO Clause
On Track | Green | HSE | Operations | 6.2 / 45001
Completed | Amber | SEC | Commercial | 6.2 / 18788
In Progress | Red | QMS | Compliance | 6.2 / 28007
Not Started | Grey | INT | HR | 6.2 / 28000
At Risk |  |  | Senior Management | 6.2 / 9001
Overdue |  |  | Finance | 6.2 / Multi
Deferred |  |  |  | 6.2 / 7.2
6.2 / 7.5
6.2 / 9.1
6.2 / 9.3
6.2 / 10.1