## Dashboard
SEAGULL MARITIME — COMBINED WORK PROGRAMME
ISO 45001 Certification ¦ Shell Audit Remediation ¦ Management System Transition
Document Reference: | SM/INT/CMP/002 v3.0
Programme Title: | Combined Work Programme — Management System Build, ISO 45001 Certification & Shell Audit Remediation
Programme Owner: | Group Compliance Director
Contributors: | CEO, WAF Operations Director, Senior Operations Manager, HR & Training Manager
Shell Review Target: | TBC May 2026
45001 Certification Target: | Audits completed 21/04/2026 - awaiting confirmed report and certificate
Created: | 23 March 2026
Last Updated: | 23 April 2026 (S47 wrap)
PROGRAMME METRICS
69 |  | 55 | 3 |  | 2 |  | 0
Total Actions |  | Completed | In Progress |  | Pending |  | Overdue
SHELL FINDINGS STATUS |  |  |  | PHASE PROGRESS
F1 | Malta License to Operate |  | Ongoing | Phase 1: Foundation |  | Feb 2026 | Backdated
F2 | Risk Management / 45001 |  | In Progress | Phase 2: Core Build |  | Mar 2026 | Active
F3 | Media & Social Media Policy |  | CA In Progress | Phase 3: Implementation |  | Apr 2026 | Upcoming
F4 | Insurance Documentation |  | Completed | Phase 4: Certification |  | May 2026 | Upcoming
F5 | Nigerian Navy MOU |  | Completed
F6 | VPSHR Integration |  | CA Implemented
F7 | IRT Exercise |  | Pending
KEY DATES
Shell Audit Conducted |  |  |  | 20-21 January 2026
CMP-002 Originated |  |  |  | January 2026
Phase 1 Effective Date |  |  |  | 01 February 2026
Phase 2 Effective Date |  |  |  | 01 March 2026
45001 Stage 1 (Documentation) |  |  |  | Mid-April 2026
Shell Review / Phase 4 |  |  |  | First week May 2026
45001 Stage 2 (Implementation) |  |  |  | TBC — requires travel

## Master Programme
COMBINED WORK PROGRAMME — MASTER TASK LIST
Ref | Task Description | 45001 Clause | Shell Ref | Phase | Owner | Start Date | Target Date | Status | Evidence / Deliverable | Comments
PHASE 1: FOUNDATION
1.01 | Define OH&S Management System Scope | 4.3 |  | 1 | Compliance Director | 01/02/2026 | 07/02/2026 | Completed | SM/HSE/DOC/001 Scope Statement v1.0 | COMPLETED S14 — 30 Mar 2026. Sent to Libero with updated application.
1.02 | Context of the Organisation — SWOT/PESTLE for H&S | 4.1 |  | 1 | Compliance Director | 01/02/2026 | 10/02/2026 | Completed | SM/INT/DOC/002 Context Analysis v1.0 + v2.0 | COMPLETED S14 — 30 Mar 2026. v1.0 pre-war baseline, v2.0 Iran war emergency review. Moved to INT prefix (cross-cutting). Renumbered from DOC/001 to DOC/002.
1.03 | Interested Parties Register (inc. VPSHR stakeholders) | 4.2 | F6 | 1 | Compliance Director | 03/02/2026 | 10/02/2026 | Completed | SM/HSE/REG/001 Interested Parties Register v1.0 | COMPLETED S14 — 30 Mar 2026. 21 parties, Power/Interest Matrix, Iran conflict flagged. Colour-coded dropdowns.
1.04 | OH&S Policy — update/reissue with VPSHR commitments | 5.2 | F6 | 1 | Compliance Director | 05/02/2026 | 12/02/2026 | Completed | SM/HSE/POL/001 OH&S Policy v1.0 | COMPLETED S14 — 30 Mar 2026. Clause 5.2 mandatory + Seagull-specific commitments. Signature blocks for CEO/GCD. CEO approved.
1.05 | Legal Requirements Register | 6.1.3 | F1 | 1 | Compliance Director | 03/02/2026 | 14/02/2026 | Completed | SM/HSE/REG/002 Legal and Regulatory Requirements Register v1.0 SM/SEC/REG/001 Flag State Requirements Register v1.0 SM/INT/REG/007 External Standards and References Register v1.0 SM/HSE/PRO/002 Legal and Regulatory Compliance Procedure v1.0 SM/INT/PRO/004 External References and Standards Procedure v1.0 | Full legal compliance infrastructure built 01/04/2026. 3 registers (37 flags, 37 legal entries, 27 standards) + 2 procedures. All "Not Assessed" — responsible person review before audit. CWP task added.
1.06 | Management of Change Procedure | 8.1.3 | OFI1 | 1 | Compliance Director | 10/02/2026 | 17/02/2026 | Completed | SM/INT/PRO/013 v1.0 + SM/INT/FORM/003 + SM/INT/REG/009. Supersedes SM/PRO/CHA/001. | Shell OFI #1 direct requirement. ISO 45001 8.1.3. Full MoC procedure with form, register, impact assessment, emergency changes, post-implementation review. S33.
1.07 | Media & Social Media Policy — finalise and issue | 7.4 | F3 | 1 | Compliance Director | 01/02/2026 | 07/02/2026 | Completed | SM/INT/POL/001 Media Policy | COMPLETED S24 — Policy rebuilt in new template format. All 17 policies received header/footer restoration and signature date update (02/04/2026). CEO approval confirmed.
1.08 | D&A Policy — finalise scope across all personnel types | 5.2 | OFI7 | 1 | Compliance Director Legal | 10/02/2026 | 21/02/2026 | Completed | SM/INT/POL/010 Drugs and Alcohol Policy v1.0 SM/INT/PRO/021 Drugs and Alcohol Testing Procedure v1.0 | COMPLETED S35 — 8 Apr 2026. Full D&A policy + testing procedure. Addresses Shell OFI-7. All personnel types covered. Random, for-cause, and post-incident testing.
1.09 | Document Control Procedure — update for new referencing system | 7.5 |  | 1 | Compliance Director | 10/02/2026 | 14/02/2026 | Completed | SM/INT/PRO/002 Control of Documents v1.0 | COMPLETED — Built from template, migrated ref (Option A). Old SM/PRO/DOC/001 withdrawn.
1.10 | Sanctions check procedure — embed US checks, update register |  | OFI3 | 1 | Compliance Director | 10/02/2026 | 19/02/2026 | Completed | OFAC embedded in SM/INT/POL/002 (Code of Conduct sanctions section), SM/INT/DOC/003 (Risk Screening Tool Dimension 3), Sanctions Screener (30,604 entries: OFAC SDN + UK + EU). SM/INT/REG/007 updated. | COMPLETED S36 — 8 Apr 2026. US/OFAC sanctions explicitly named in Code of Conduct, screening tool, and sanctions database. Shell OFI-3 addressed. S41: Live sanctions infrastructure overhaul — refresh_sanctions.py v2 fetches OFAC SDN + UK FCDO + EU FSF; sanctions-screener.html rebuilt (14MB → 31KB, fetches canonical JSON); risk-screening-tool.html now uses real Levenshtein fuzzy matching against 35,300-entry sanctions DB. Scheduled weekly refresh Monday 3am Dubai.
1.11 | Malta exemption — chase and document |  | F1 | 1 | Legal | 26/01/2026 | Ongoing | Ongoing | Malta exemption letter | Escalated, awaiting response
1.12 | Insurance documentation alignment (UK vs Malta) |  | F4 | 1 | Legal | 26/01/2026 | 10/02/2026 | Completed | Updated insurance docs | COMPLETED
1.13
1.14 | Internal Audit Programme Review — self-raise NCR for 2025 gaps | 9.2 |  | 1 | Compliance Director | 10/02/2026 | 10/02/2026 | Completed | SM/INT/RPT/001 IA Programme Review and Gap Analysis | COMPLETED — Gap analysis produced, NCRs self-raised in register.
1.15 | Internal Audit Schedule 2026 — design and approve | 9.2 |  | 1 | Compliance Director | 10/02/2026 | 14/02/2026 | Completed | SM/INT/REG/003 Internal Audit Schedule 2026 | COMPLETED — 12-month rolling schedule designed and approved.
PHASE 2: RISK FRAMEWORK & CORE PROCEDURES
2.01 | Hazard Identification & Risk Assessment framework | 6.1.1 6.1.2 | F2 | 2 | Compliance Director | 01/03/2026 | 10/03/2026 | Completed | SM/HSE/PRO/001 Hazard ID & Risk Assessment Procedure v1.0 SM/HSE/RA/002-009 (8 Risk Assessments, 130 hazards) SM/CAM/BRAG/001-010 (10 BRAGs) SM/HSE/MS/001 Method Statement: Test Fire at Sea v1.0 | SM/HSE/PRO/001 Hazard ID & Risk Assessment Procedure v1.0 SM/HSE/RA/002-009 (8 Risk Assessments, 130 hazards) SM/CAM/BRAG/001-008 (8 BRAGs)
2.02 | OH&S Objectives, Targets & KPIs | 6.2 |  | 2 | Compliance Director | 03/03/2026 | 10/03/2026 | Completed | SM/INT/REG/006 - Company Objectives Register v1.0 (30 objectives across HSE/SEC/QMS/INT) | Linked to monitoring (9.1)
2.03 | Roles, Responsibilities & Authorities matrix | 5.3 |  | 2 | Compliance Director | 03/03/2026 | 07/03/2026 | Completed | SM/INT/DOC/005 Roles, Responsibilities and Authorities Matrix (RACI) v1.0 | COMPLETED S34 — 8 Apr 2026. 48 functions, 11 roles, 7 categories. Excel with dashboard.
2.04 | Worker Consultation & Participation procedure | 5.4 |  | 2 | Compliance Director | 05/03/2026 | 12/03/2026 | Completed | SM/INT/PRO/014 Worker Consultation and Participation Procedure v1.0 | COMPLETED S34 — 8 Apr 2026. 10 sections. Consultation + participation mechanisms, Safety App, BRAGs, debriefs.
2.05 | Emergency Preparedness & Response procedure | 8.2 | F7 | 2 | Compliance Director | 05/03/2026 | 14/03/2026 | Completed | SM/HSE/PRO/003 Emergency Preparedness and Response Procedure v1.0 | COMPLETED S34 — 8 Apr 2026. 12 sections. Umbrella framework linking PRO-006, BCP, SOPs. IRT exercise target: May 2026.
2.06 | Incident Investigation procedure | 10.1 |  | 2 | Compliance Director | 10/03/2026 | 17/03/2026 | Completed | SM/INT/PRO/006 Incident and Crisis Management v1.0 SM/INT/PRO/001 NCR/OFI/CAPA Management v1.0 SM/OPS/SOP/001 Section on incident procedures Safety App for reporting | COMPLETED — Incident investigation covered by PRO-006 (investigation framework), PRO-001 (NCR/CAPA lifecycle), IOR SOP incident sections, and Safety App reporting. 45001 Cl. 10.1 satisfied.
2.07 | NCR & Corrective Action procedure | 10.2 |  | 2 | Compliance Director | 10/03/2026 | 17/03/2026 | Completed | SM/INT/PRO/001 NCR/OFI/CAPA Management v1.0 SM/INT/REG/004 NCR/OFI/CAPA Register v1.0 SM/INT/FORM/001 Non-Conformance Report Form v1.0 | COMPLETED — Full suite: procedure + register + form. Ref changed from planned HSE/PRO to INT/PRO/001 (cross-cutting, not H&S specific).
2.08 | VPSHR integration — embed into operational procedures |  | F6 | 2 | Compliance Director | 10/03/2026 | 21/03/2026 | Completed | VPSHR embedded across all operational procedures and annexes: • SM/OPS/SOP/001 + Annexes A, B, C, D, E, F, G, H (IOR — full suite) • SM/OPS/SOP/002 + Annex A (WAF) • SM/OPS/PRO/001 Rules on the Use of Force • SM/INT/POL/002 Code of Conduct • SM/TRG/DOC/001-002 Human Rights training courses • SM/SEC/POL/002 Human Rights Policy | COMPLETED S43 — 17 Apr 2026. All IOR SOP Annexes A–H confirmed issued with VPSHR integration. Full operational-procedural and training coverage. GCD verified 17 April 2026. Shell F6 closure evidence.
2.09 | Procurement & contractor H&S requirements | 8.1.4 |  | 2 | Compliance Director | 14/03/2026 | 08/04/2026 | Completed | SM/INT/PRO/017 Supplier, Contractor and Procurement Management v1.0 SM/INT/FORM/004-006 (Supplier forms + SCAR + Checklist) SM/INT/REG/010 Supplier and Subcontractor Register v1.0 SM/SEC/PRO/004-005 (SEV procedures) SM/SEC/FORM/001-004 (SEV forms) | COMPLETED S34 — 8 Apr 2026. Full procurement suite: procedure + Word forms + Excel checklists + register + SCAR. SEV docs corrected and unified. Evidence ref corrected from HSE/PRO/006.
2.10 | SEV Minimum Standards document |  | OFI6 | 2 | WAF Ops Director | 10/03/2026 | 28/03/2026 | Completed | SM/SEC/PRO/004, SM/SEC/PRO/005, SM/SEC/FORM/001, SM/SEC/FORM/002 | COMPLETED S28 — 04 Apr 2026. Full SEV minimum standards defined: 27 vessel docs (V01-V27), 11 provider docs (P01-P11), source-attributed to OCIMF/Shell/SOLAS/ISO. Matching forms rebuilt.
2.11 | Vessel delay wording — SOP amendment issued |  | OFI4 | 2 | Compliance Director | 01/03/2026 | 05/03/2026 | Completed | Annex D (Vessel Delay) and Annex E (UKMTO) issued | SOP annex wording amended. Formal SOP reissue and training pending. OFI-010 in NCR register (Completed).
2.12 | UKMTO incident reporting — SOP amendment issued |  | OFI5 | 2 | Compliance Director | 01/03/2026 | 05/03/2026 | Completed | Annex D (Vessel Delay) and Annex E (UKMTO) issued | SOP annex updated with UKMTO as primary reporting. Formal SOP reissue and training pending. OFI-011 in NCR register (Completed).
2.13 | Nigerian Navy MOU — training review |  | F5 | 2 | Compliance Director HR & Training | 03/03/2026 | 14/03/2026 | Completed | Training review record | Closed 12/03/2026. MOU reviewed against WAF competence framework. No operational training component required — obligations held by WAF Country Manager and Nigeria team as BAU.
2.14 | Management Review Procedure — update to 45001 spec | 9.3 | OFI2 | 2 | Compliance Director | 14/03/2026 | 08/04/2026 | Completed | SM/INT/PRO/003 Management Review | Shell OFI #2 + 45001 requirement
2.15 | Internal Audit Procedure — confirm 45001 compliance | 9.2 |  | 2 | Compliance Director | 17/03/2026 | 24/03/2026 | Completed | SM/INT/PRO/003 Internal Audit v1.0 | COMPLETED — Built from template, migrated ref (Option A). Old SM/PRO/IA/001 withdrawn.
2.16
2.17 | Risk assessments created and distributed | 6.1.2 | F2 | 2 | Compliance Director Relevant managers | 01/03/2026 | 21/03/2026 | Completed | Completed risk assessments (RA-003/004 pattern): SM/HSE/RA/002-010 (9 RAs, 144 hazards) + SM/CAM/BRAG/001-010 + SM/HSE/MS/001 | All 9 ISO 45001 H&S RAs built (SM/HSE/RA/002-010): Vessel Transfer, Security Duties, Secure Accommodation, Vessel Transit, Small Arms Handling, Office Workplace, Remote Working, Heat Stress, Night Operations — 144 hazards total (was 130 before Night Ops added S18). 9 matching BRAGs in For Distribution. Test Fire at Sea suite added S39: SM/CAM/BRAG/010 + SM/HSE/MS/001 Method Statement — covers pre-transit weapon test fire hazards.
2.18 | Continual Improvement procedure | 10.3 |  | 2 | Compliance Director | 21/03/2026 | 28/03/2026 | Completed | SM/INT/PRO/015 Continual Improvement Procedure v1.0 | COMPLETED S34 — 8 Apr 2026. 11 sections. Sources, prioritisation, leading/lagging indicators, Management Review input.
PHASE 3: IMPLEMENTATION & EVIDENCE
3.01 | Training needs analysis — all new/amended procedures | 7.2 | F2 | 3 | Compliance Director HR & Training | 01/04/2026 | 07/04/2026 | Completed | SM/INT/PRO/010 Training and Competence Procedure approved. TNA framework established. SM/INT/REG/008 Training and Competence Matrix v1.0 — 20 courses × 41 personnel mapped.
3.02 | Training programme — design and schedule rollout | 7.2 7.3 | F2, F3, F6 | 3 | Compliance Director HR & Training | 01/04/2026 | 10/04/2026 | Completed | SM/INT/PRO/010 approved. Course design in progress. SM/TRG/DOC/001 — Human Rights PCASP Training v1.0 (28 slides) SM/TRG/DOC/002 — Human Rights Staff & Management Training v1.0 (28 slides) Emergent LMS: AI quiz generation, certificate sharing, leaderboard, mandatory courses matrix, Operations role split (IOR/WAF). SEV & Suppliers course LIVE. WAF ops set as mandatory. | S25 courses built. S28 LMS features: share certificates (public links), admin exclusion on leaderboard, mandatory course compliance matrix, Operations-IOR/Operations-WAF role split. All tests passing.
3.03 | Training rollout — Batch 1 (core H&S, MoC, risk) | 7.2 | F2, OFI1 | 3 | Compliance Director HR & Training | 07/04/2026 | 14/04/2026 | Completed | LMS LIVE — 21 courses deployed. Staff onboarding in progress. Pavel deadline: all mandatory courses by 20 Apr 2026. | COMPLETED S36 (status flipped S47, 23 Apr 2026) — LMS launched 8 Apr 2026. All courses live. Department managers accountable for team completion. Human Rights + H&S priority for Shell evidence.
3.04 | Training rollout — Batch 2 (media, VPSHR, D&A, ops) | 7.2 | F3, F6, OFI7 | 3 | HR & Training | 14/04/2026 | 21/04/2026 | Completed | LMS LIVE — Batch 2 courses (media, VPSHR, D&A, ops) all on LMS. Mandatory completion deadline: 20 Apr 2026. | COMPLETED S36 (status flipped S47, 23 Apr 2026) — All Batch 2 courses on LMS. Pavel set 20 Apr 2026 mandatory deadline. Social Media, Human Rights, D&A all deployed.
3.05 | PCASP briefing to Masters — formalise and distribute |  | OFI8 | 3 | Compliance Director WAF Ops | 01/04/2026 | 07/04/2026 | Completed | Formal briefing document + distribution record | COMPLETED S36 — 9 Apr 2026. Formal briefing document distributed to all Masters.
3.06 | IRT Exercise — plan, conduct, document | 8.2 | F7 | 3 | Compliance Director | 07/04/2026 | 08/04/2026 | Completed | SM/HSE/RPT/001 IRT Exercise Report (Office Fire, Piraeus, 27/03/2026). 4 OFIs raised (OFI-013 to OFI-016). | Critical Shell finding
3.07 | Management Review #1 — conduct to 45001 spec | 9.3 | OFI2 | 3 | Compliance Director Senior management | 14/04/2026 | 18/04/2026 | Completed | SM-INT-MRM-001 Management Review Minutes v1.0 | COMPLETED — Management review conducted. Minutes drafted, formatting polish pending.
3.08 | Internal Audit — schedule and commence cycle | 9.2 |  | 3 | Compliance Director | 14/04/2026 | 25/04/2026 | Completed | SM-IA-26-001 Document Control Audit Report SM-IA-26-002 Risk Management Audit Report SM/INT/REG/003 Audit Schedule SM/INT/REG/004 NCR Register | COMPLETED S47 — 2026 audit cycle active; 2 audits completed with reports and CMPs. Findings tracked in NCR register. Cycle ongoing per schedule.
3.09 | Competence assessment matrices — high-risk roles | 7.2 |  | 3 | Compliance Director HR & Training | 07/04/2026 | 18/04/2026 | Completed | SM/INT/REG/008 Training and Competence Matrix v1.0 — 20 courses, 3 role categories, 41 shore-based personnel. Derived from SM/INT/PRO/010 sections 7.1–7.3.
3.10 | Legal register — responsible person review and compliance assessment | 6.1.3 9.1.2 |  | 3 | Compliance Director | 15/04/2026 | 30/04/2026 | Completed | SM/HSE/REG/002 Legal and Regulatory Requirements Register v1.0 SM/SEC/REG/001 Flag State Requirements Register v1.0 SM/INT/REG/007 External Standards and References Register v1.0 | COMPLETED S36 — Registers built and populated. Ongoing compliance assessment tracked internally. Responsible person review in progress.
3.11 | MS Transition — CMP-003 formally initiated |  |  | 3 | Compliance Director | 01/04/2026 | 01/04/2026 | In Progress | SM/INT/CMP/003 | See MS Transition sheet
3.12 | Nigerian Navy MOU training completed |  | F5 | 3 | HR & Training | 07/04/2026 | 14/04/2026 | Completed | Training records | Closed 12/03/2026 under 2.13 — no operational training requirement identified. MOU relationship administered by WAF Country Manager and Nigeria team.
PHASE 4: CERTIFICATION & REVIEW READY
4.01 | 45001 Stage 1 Audit (Documentation Review) — Libero | 全 |  | 4 | Compliance Director | 21/04/2026 | 25/04/2026 | Completed | Stage 1 audit report | COMPLETED — ISO 45001 Stage 1 Documentation Review passed early April 2026 (remote/desktop review, clean pass no NCs). Libero. Darren fronted solo as GCD.
4.02 | Stage 2 on site audit nonconformities — address any findings |  |  | 4 | Compliance Director | 25/04/2026 | 02/05/2026 | In Progress | Corrective action records | IN PROGRESS — Stage 1 (doc review, early April 2026) passed clean. Stage 2 (on-site, 21 April 2026) passed with 1 minor NC raised. Minor NC does not block certification — response in progress.
4.03 | Shell review preparation — compile evidence pack |  | F1-F7 | 4 | Compliance Director | 25/04/2026 | 01/05/2026 | Completed | shell.seagullmaritimeltd.com — custom Shell audit response portal (6 chapters: Audit, Platform, Culture, Live, Intelligence, Human Rights). Gate code SHELL-SEA-2026 shared with Dennis Kerlin, Andy Keane, Neil Murray in response email (17/04/2026, 14:47 Dubai). Also hosts standalone Culture showcase, full F1-F7 closure evidence, rolling document update timeline, Human Rights (VPSHR) pillar framework, LMS/HSE App demo credentials. | COMPLETED S43 — 17 Apr 2026. Evidence pack delivered as interactive portal, not document dump. Shell response email sent 14:47 Dubai 17/04/2026 with portal link + gate code. Pavel, Richard, Kfir on cc. No onsite verification required pending Shell review (TBC May 2026).
4.04 | Shell review — TBC May 2026 |  | F1-F7 | 4 | Compliance Director | 04/05/2026 | 08/05/2026 | Pending | Shell review outcome | Shell date updated S40 (16 Apr 2026): Dennis Kerlin's 20 Feb 2026 email stated 'approx 3-4 months' — no fixed date confirmed. Target window TBC May 2026.
4.05 | Post-Shell review actions (if any) |  |  | 4 | Compliance Director | TBC | TBC | Pending | Action tracker
4.06 | 45001 Stage 2 Audit planning |  |  | 4 | Compliance Director | TBC | TBC | Completed | Stage 2 plan + travel arrangements | COMPLETED S47 — ISO 45001 Stage 2 on-site audit conducted 21 April 2026 in Athens (Darren fronted as GCD). Passed with 1 minor NC raised (live under 4.02). Certification proceeds.
4.07 | Continual improvement cycle — documented evidence | 10.3 |  | 4 | Compliance Director | 01/05/2026 | Ongoing | In Progress | Improvement log entries
PHASE 5: GROUP GOVERNANCE LAYER & COMPLIANCE PLATFORM
5.01 | ESG Policy — group-level foundational | All / 45001 / 18788 / 28007 / 28000 |  | 5 | Compliance Director | 17/04/2026 | 17/04/2026 | Completed | SM/INT/POL/011 ESG Policy v1.0 + VAN/INT/POL/010 ESG Policy v1.0 (Vanguard mirror) | COMPLETED S42 — 17 Apr 2026. Group-level umbrella pulling existing Environmental, Human Rights, Code of Conduct, Anti-Bribery into single strategic statement. Signed Pavel (CEO) + Darren (GCD). Lean foundational — evolves as ESG reporting capability matures.
5.02 | Sanctions Policy — standalone with live tooling wired in | 18788 / 28000 / 28007 / 9001 / OFAC / UK OFSI / EU FSF / UN |  | 5 | Compliance Director | 17/04/2026 | 17/04/2026 | Completed | SM/INT/POL/012 Sanctions Policy v1.0 + VAN/INT/POL/011 (Vanguard mirror, tool-agnostic) | COMPLETED S42 — 17 Apr 2026. Explicit OFAC / UK OFSI / EU FSF / UN regimes. Names the live Sanctions Screener + Risk Screening Tool + 35K-entry DB + weekly refresh. Closes OFI-003.
5.03 | Conflict of Interest Policy + Register | 9001 / 18788 / 28007 / 28000 / ICoCA |  | 5 | Compliance Director | 17/04/2026 | 17/04/2026 | Completed | SM/INT/POL/013 Conflict of Interest Policy v1.0 + SM/INT/REG/011 CoI Register v1.0 (stub, live for declarations) + VAN/INT/POL/012 (Vanguard mirror) | COMPLETED S42 — 17 Apr 2026. Full declaration-management-review lifecycle. REG/011 ready for live declarations. Includes Operational Decision-Making Conflicts as explicit category (manages director-level bypass pattern).
5.04 | D&A Policy — canonical format rebuild | 45001 / 18788 |  | 5 | Compliance Director | 17/04/2026 | 17/04/2026 | Completed | SM/INT/POL/010 Drugs and Alcohol Policy v1.0 (format-only reissue, content verbatim) | COMPLETED S42 — 17 Apr 2026. Content unchanged; rebuilt from POL/008 Social Media template to fix 9-row doc control → canonical 10-row with Applicable Entities, cover page removed, section headings unified. Old format backup in Misc/. PDF pushed to all portal locations.
5.05 | KYC Framework — portal tool for Finance-led KYC | 9001 / 18788 / AML |  | 5 | Compliance Director | 17/04/2026 | 17/04/2026 | Completed | kyc-framework.html portal tool (campaign/tools/), linked on portals homepage | COMPLETED S42 — 17 Apr 2026. Draft v0.1. 10 sections pattern-matched to DD portal. Finance-led population, Compliance policy overlay. Wires in live Sanctions Screener + 5 live policies. Pitched to CEO/CFO on launch call.
5.06 | Campaign Portal Launch + Ecosystem Integration | All |  | 5 | Compliance Director | 17/04/2026 | 17/04/2026 | Completed | portals.seagullmaritimeltd.com/campaign — LIVE with 18+ doc library, BUL/001-003, 5 tools, threat banner, unified nav | COMPLETED S42 — 17 Apr 2026. Campaign portal launched. Pavel endorsement + mandatory directive. 5 compliance tools standardised to canonical nav.
5.07 | Shell Portal — lockdown + standalone Culture showcase | Shell audit evidence |  | 5 | Compliance Director | 17/04/2026 | 17/04/2026 | Completed | shell.seagullmaritimeltd.com/culture/ standalone locked copy + Ch03 repointed internally + Ch05/Ch06 reorder + live.html evergreen + platform.html LMS/HSE demo creds | COMPLETED S42 — 17 Apr 2026. Culture showcase built as locked dead-end inside Shell domain (no outbound escape). Human Rights promoted to Ch05, Intelligence (Rich/Olga TBP) to Ch06 as coming-soon. Risk Screening Tool de-linked to keep portal perimeter clean. LMS + HSE demo credentials surfaced (demo@seagullsecurity.com / demo2026).
5.08 | Master's Evaluation Platform (HSE App module) | 28007 / 18788 (9.1) / 45001 (10.3) |  | 5 | GCD / Ops | 17/04/2026 | 17/04/2026 | Completed | SMS/FORM/MEV/001 auto-generated + HSE App Master portal module + multi-tenant CSO dashboards | COMPLETED S42 — 17 Apr 2026 (Darren built in Emergent). Transient-access Master login per transit, 3-step evaluation wizard, auto-PDF to Ops/GCD. Client CSO dashboards tenant-scoped. Live at report.seagullmaritimeltd.com. Seagull-owned IP (exportable from Emergent). Pitched on launch call.
5.09 | Shell Audit Response — submit via custom portal to Shell lead auditors | 9.3 / 10.1 | F1-F7 | 5 | Compliance Director | 17/04/2026 | 17/04/2026 | Completed | Response email sent 17/04/2026 14:47 Dubai. Recipients: Dennis Kerlin (Lead), Andy Keane, Neil Murray + Pavel / Richard / Kfir on cc. Portal URL shell.seagullmaritimeltd.com. Gate code SHELL-SEA-2026. | COMPLETED S43 — 17 Apr 2026. Major milestone. Shell review now awaited TBC May 2026. Portal live and self-updating. No document dump required — portal is the response.
5.10 | Vitol WAF Due Diligence — LSC auditor review and Vitol principal sign-off | 28000 / 28007 / 18788 / DD | — | 5 | Compliance Director / Ops | 03/04/2026 | 17/04/2026 | Completed | Portal: portals.seagullmaritimeltd.com/dd/waf/. SM/SEC/PRO/002 v1.1, SM/SEC/DOC/002, SM/SEC/FORM/002 v1.1, SM/OPS/SOP/002 + Annex A. LSC (Aleksejs Sidorenko, MD) confirmed no further questions 17/04/2026 13:41 Dubai. Vitol (Neeraj Sareen) confirmed no onsite verification required 17/04/2026 14:13 Dubai. | COMPLETED S43 — 17 Apr 2026. WAF DD work from S26–S28 validated. Tasos Blanos introduced as ongoing POC. Future audit deferred by Vitol to 'when time allows'.
5.11 | Full tracker reconciliation and Document Register rebuild | 7.5 / 9.1 | — | 5 | Compliance Director | 17/04/2026 | 17/04/2026 | Completed | Document Register v2.3 → v2.4 (15 new entries added: Test Fire suite, Emergency Contact annexes, 9 training course decks). Sequence Tracker corrected (HSE/RA, OPS/PRO, OPS/FORM, TRG/DOC). CWP, NCR Register, Reconciliation Matrix, IA-001/002 CMPs all reviewed and updated to current state. Outstanding items list curated (stale items struck off). | COMPLETED S43 — 17 Apr 2026. Full sweep ordered by GCD after discovery that handover outstanding-item list had accumulated stale entries across multiple sessions. New discipline locked in: fresh curation each session, no copy-forward accumulation.

## Shell Findings
SHELL AUDIT FINDINGS — DETAILED TRACKER
Shell Maritime Security Due Diligence Audit — 20/21 January 2026 ¦ Auditors: Dennis Kerlin (Lead), Andy Keane, Neil Murray
Ref | Finding Description | Shell Recommendation | Seagull Required Actions | Owner | Start Date | Target Date | Status | Comments / Evidence
F1 | License to Operate Maltese exemption documentation (S.L. 480.05 / Arms Act) | Obtain and maintain written confirmation from Maltese government body confirming exemption status | Contact Maltese authorities — request exemption letter | Legal | 26/01/2026 | 13/02/2026 | Ongoing | Request made via company secretary, escalated Legal and regulatory infrastructure built 01/04/2026 (3 registers + 2 procedures). Malta exemption still outstanding.
|  |  | On receipt, provide to Shell | Compliance Director | TBC | TBC | Pending | Dependent on Malta response
|  |  | Add to company structure folder in DD folders | Compliance Administrator | TBC | TBC | Pending
|  |  | Add to company legal documentation | Legal | TBC | TBC | Pending
F2 | Risk Management System Lack of structured risk framework for identification, assessment, control and mitigation across WAF and IOR | Develop unified org-wide risk management framework inc. ISO 45001. Cover all operational environments, integrate HSSE, document within SOPs | ISO 45001 certification request — Libero | Compliance Director | 05/02/2026 | 10/02/2026 | Completed | Audit booked — postponed from 17 Mar (conflict zone)
|  |  | Build OH&S Management System to 45001 | Compliance Director | 01/02/2026 | 18/04/2026 | Completed | COMPLETED S36 — All 25 ISO 45001 clauses satisfied. Full management system operational. Stage 1 submission pack ready.
|  |  | Risk assessments created and distributed | Compliance Director Relevant managers | 01/03/2026 | 21/03/2026 | Completed | 8x RA-003 pattern RAs (SM/HSE/RA/002-009) completed 31/03/2026. 130 hazards. 8 matching BRAGs. SM/HSE/RA/010 Night Operations RA (14 hazards) + BRAG added 01/04/2026. Total: 9 RAs, 144 hazards, 9 BRAGs.
|  |  | Policies and procedures distributed | Compliance Director | 01/03/2026 | 10/04/2026 | In Progress | IN PROGRESS — LMS courses distribute procedures. DD portals host all current docs. Campaign portal document library live. Formal For Distribution folders maintained.
|  |  | Training & awareness programmes created | Compliance Director HR & Training | 01/04/2026 | 21/04/2026 | Completed | COMPLETED S36 — LMS live with 21 courses. 9 training slide decks built. Training matrix (20 courses x 41 personnel). AI quizzes, certificates, leaderboard.
|  |  | Relevant SOPs updated | Compliance Director | 01/03/2026 | 21/03/2026 | Completed | COMPLETED — IOR SOP + Annexes A/H updated (S21). WAF SOP + Annex A updated (S26). RUF procedure updated (S22). VPSHR, BMP-MS, Safety App refs throughout.
|  |  | Training programmes released and ongoing | Compliance Director HR & Training | 07/04/2026 | 21/04/2026 | In Progress | IN PROGRESS S36 — LMS launched 8 Apr 2026. Pavel mandatory deadline: 20 Apr. Staff onboarding this week. Priority: Human Rights + H&S for Shell.
F3 | Media & Social Media Policy No formal policy governing media interactions or social media use | Develop and implement a media and social media policy with clear guidelines, training, and accountability | Draft media & social media policy | Compliance Director | 01/02/2026 | 07/02/2026 | Completed | Draft completed
|  |  | Finalise and obtain CEO approval | Compliance Director CEO | 07/02/2026 | 14/02/2026 | Completed | COMPLETED — Policy rebuilt in new template format S24. CEO approval confirmed. Signature date 02/04/2026.
|  |  | Issue to all personnel | Compliance Director | 14/02/2026 | 21/02/2026 | Completed | COMPLETED S24 — Policy rebuilt in new template format and issued. Available on LMS as mandatory training course (Social Media Policy Awareness) from 8 Apr 2026. Awareness/training rollout tracked separately below.
|  |  | Training and awareness rollout | Compliance Director | 07/04/2026 | 14/04/2026 | In Progress | IN PROGRESS S36 — Social Media course on LMS. Mandatory completion deadline 20 Apr 2026.
F4 | Insurance Documentation Personal insurance listed under UK entity, operations under Maltese entity | Ensure insurance documentation is aligned with the operating entity | Align insurance documentation with operating entity | Legal | 26/01/2026 | 10/02/2026 | Completed | COMPLETED — documentation aligned
F5 | Nigerian Navy MOU No formal MOU with Nigerian Navy for WAF operations | Obtain formal MOU or equivalent documentation | Obtain Nigerian Navy MOU | WAF Ops Director | 26/01/2026 | 28/02/2026 | Completed | Seagull Maritime — Nigerian Navy MOU (05 Feb 2026) provided to Shell as F5 closure evidence 6 Feb 2026.
|  |  | Training review on MOU requirements | Compliance Director HR & Training | 03/03/2026 | 14/03/2026 | Completed | Closed 12/03/2026. MOU reviewed against WAF competence framework. No operational training component required — MOU obligations held by WAF Country Manager and Nigeria team as BAU within existing WAF SOP / RUF framework.
F6 | VPSHR Adoption Voluntary Principles on Security and Human Rights not formally integrated | Formally adopt VPSHR and integrate into procedures, training, and governance | Review VPSHR requirements against current procedures | Compliance Director | 10/02/2026 | 21/02/2026 | Completed | VPSHR integrated into IOR SOP (S4), Annexes A/H, RUF procedure, Code of Conduct. SM/INT/PRO/010 includes VPSHR training section.
|  |  | Update OH&S Policy with VPSHR commitments | Compliance Director | 05/02/2026 | 12/02/2026 | Completed | SM/HSE/POL/001 v1.0 — VPSHR commitments embedded in Sections 2 and 3. Completed S14 30 Mar 2026.
|  |  | Integrate VPSHR into operational SOPs | Compliance Director | 10/03/2026 | 21/03/2026 | Completed | COMPLETED S21-S28 — VPSHR integrated into IOR SOP + Annexes A/H, WAF SOP + Annex A, RUF procedure, Code of Conduct. Remaining: IOR Annexes B-G (content migration).
|  |  | VPSHR training rollout | HR & Training | 14/04/2026 | 21/04/2026 | In Progress | IN PROGRESS S36 — SM/TRG/DOC/001 (PCASP) + DOC/002 (Staff) Human Rights courses on LMS. Pavel identified as priority for Shell. Mandatory deadline 20 Apr. PCASP rollout will take significant time so will have to remain in progress
F7 | IRT Exercise No documented Incident Response Team exercise conducted | Conduct and document an IRT exercise demonstrating preparedness | Define IRT exercise scope and objectives | Compliance Director | 07/04/2026 | 08/04/2026 | Completed | SM/HSE/RPT/001 completed. Scenario: office fire Piraeus.
|  |  | Plan exercise scenario | Compliance Director | 10/04/2026 | 08/04/2026 | Completed | Fire at Piraeus office — electrical distribution room.
|  |  | Conduct IRT exercise | Compliance Director Operations team | 14/04/2026 | 08/04/2026 | Completed | Tabletop exercise 27/03/2026. 7 participants across 4 locations.
|  |  | Document exercise report and lessons learned | Compliance Director | 16/04/2026 | 08/04/2026 | Completed | SM/HSE/RPT/001 v1.0. 4 improvement actions raised as OFI-013 to OFI-016.

## Shell OFIs
SHELL AUDIT OFIs — DETAILED TRACKER
Opportunities for Improvement — Not approval contingent but expected for best practice
Ref | OFI Description | Seagull Comment | Required Actions | Owner | Start Date | Target Date | Status | Comments
OFI1 | Management of Change Formal MoC process for procedure updates | Existing CMP procedure — recognise Andy's comment re new SOP implementation, will review and amend | Review change management procedure | Compliance Director | 10/02/2026 | 17/02/2026 | Completed | SM/INT/PRO/013 v1.0 + SM/INT/FORM/003 + SM/INT/REG/009 + online form. Full suite in For Distribution S34.
|  |  | Update and reissue | Compliance Director | 17/02/2026 | 21/02/2026 | Completed | SM/INT/PRO/013 v1.0 in For Distribution. S34.
|  |  | Release to relevant departments | Compliance Director | 21/02/2026 | 28/02/2026 | Completed | Procedure + online change request form live. S33-34.
|  |  | Document change management for SOP updates | Compliance Director | 01/03/2026 | 07/03/2026 | Completed | MoC procedure covers SOP change management. S33-34.
OFI2 | Management Review Structured annual management review cycle | Have procedure and conduct reviews — will review structure and amend per audit comments | Review Management Review Procedure | Compliance Director | 14/03/2026 | 21/03/2026 | Completed | COMPLETED S34 — SM/INT/PRO/019 Management Review Procedure v1.0 built to 45001 spec. 11 input areas, 5 outputs.
|  |  | Update to 45001 spec (defined inputs/outputs) | Compliance Director | 21/03/2026 | 28/03/2026 | Completed | COMPLETED S34 — SM/INT/PRO/019 v1.0 fully 45001 compliant.
|  |  | Conduct Management Review #1 | Compliance Director Senior management | 14/04/2026 | 18/04/2026 | Completed | COMPLETED — Management review conducted. SM-INT-MRM-001 minutes drafted.
OFI3 | Sanctions Listings Embed US sanctions checks into compliance workflows | Checks conducted but wording does not cover US sanctions. Lists not in external references register | Review documents where sanctions listed | Compliance Director | 10/02/2026 | 19/02/2026 | Completed | COMPLETED S36 — OFAC/US sanctions explicitly embedded in Code of Conduct (dedicated section), Risk Screening Tool (Dimension 3), Sanctions Screener (30K+ entries). External refs register updated.
|  |  | Update external references register | Compliance Administrator | 17/02/2026 | 19/02/2026 | Completed | COMPLETED — SM/INT/REG/007 External Standards and References Register includes OFAC SDN, UK FCDO, EU sanctions refs.
|  |  | Update relevant documentation and issue | Compliance Director | 01/03/2026 | 07/03/2026 | Completed | COMPLETED — Code of Conduct updated with OFAC section, screening tools live, DD procedures reference sanctions requirements.
OFI4 | Vessel Delay Wording Revise wording re delaying vessels for safety/weather | SOP requires wording amendment | Update relevant SOP annex | Compliance Director | 26/01/2026 | 26/01/2026 | Completed | SOP wording amended
|  |  | Formally issue updated SOP | Compliance Director | 01/03/2026 | 05/03/2026 | Completed | COMPLETED — SM/OPS/SOP/001 v1.0 formally issued S21. Vessel delay wording in Annex D.
|  |  | Training on updated procedure | HR & Training | 07/04/2026 | 14/04/2026 | In Progress | IN PROGRESS S36 — SOP RUF course on LMS includes updated procedures. This will take significant time to rollout to all PCASP and they complete so has to remain progress
OFI5 | Vessel Defence Incident Reporting Include UKMTO notification in vessel defence incident procedures | SOP updated | Update SOP with UKMTO reporting | Compliance Director | 26/01/2026 | 26/01/2026 | Completed | SOP updated
|  |  | Formally issue updated SOP | Compliance Director | 01/03/2026 | 05/03/2026 | Completed | COMPLETED — SM/OPS/SOP/001 v1.0 formally issued S21. UKMTO reporting in Annex E.
|  |  | Training on updated procedure | HR & Training | 07/04/2026 | 14/04/2026 | In Progress | IN PROGRESS S36 — SOP course on LMS includes UKMTO reporting. This will take significant time to rollout to all PCASP and they complete so has to remain progress
OFI6 | SEV Minimum Standards Define minimum standards for Security Escort Vessels | Requires input from WAF operations team | Draft SEV minimum standards document | WAF Ops Director | 10/03/2026 | 21/03/2026 | Completed | COMPLETED S28 — 04 Apr 2026. SM/SEC/PRO/004 defines 27 vessel standards, SM/SEC/PRO/005 defines 11 provider standards, SM/SEC/FORM/001 + FORM-002 are the operational checklists. All cross-referenced to OCIMF, Shell PMSC Vetting, ISO 18788, VPSHR.
|  |  | Review and approve | Compliance Director | 21/03/2026 | 28/03/2026 | Completed | COMPLETED S28 — GCD reviewed and approved. Standards embedded in SM/SEC/PRO/004 (27 vessel docs) and SM/SEC/PRO/005 (11 provider docs).
|  |  | Issue to WAF team and vessel providers | WAF Ops Director | 01/04/2026 | 07/04/2026 | Completed | Procedures and checklists built. Formal issue to WAF team pending alongside WAF deliverables review.
OFI7 | D&A Policy Extend applicability across all personnel types | Legal currently reviewing | Legal review of D&A policy scope | Legal | 10/02/2026 | 21/02/2026 | Completed | COMPLETED S35 — SM/INT/POL/010 Drugs and Alcohol Policy v1.0 + SM/INT/PRO/021 Testing Procedure v1.0. All personnel types covered.
|  |  | Update policy to cover all personnel types | Compliance Director | 21/02/2026 | 28/02/2026 | Completed | COMPLETED S35 — SM/INT/POL/010 covers all personnel types (shore, PCASP, vessel crew, contractors).
|  |  | Issue updated policy | Compliance Director | 01/03/2026 | 05/03/2026 | Completed | COMPLETED S35 — Policy in For Distribution. Testing procedure issued alongside.
|  |  | Training rollout | HR & Training | 14/04/2026 | 21/04/2026 | In Progress | IN PROGRESS S36 — D&A awareness on LMS. This will take significant time to rollout to all personnel and they complete so has to remain progress
OFI8 | PCASP Briefing to Masters Formalise security briefing process | Briefing content prepared, needs formal distribution | Finalise formal briefing document | Compliance Director | 01/03/2026 | 07/03/2026 | Completed | Briefing document finalised. OFI-012 in NCR register (Completed).
|  |  | Distribute to all Masters | Compliance Director Ops/WAF Ops | 01/04/2026 | 07/04/2026 | Completed | See Task 3.05
|  |  | Maintain distribution record | Compliance Administrator | 07/04/2026 | Ongoing | Pending

## 45001 Clauses
ISO 45001:2018 CLAUSE COMPLIANCE REGISTER
Clause | Requirement | Shell Overlap | Status | Seagull Document / Evidence | Gap / Action Required | Programme Ref
CLAUSE 4: CONTEXT OF THE ORGANISATION
4.1 | Understanding the organisation and its context |  | Completed | SM/INT/DOC/002 v1.0 + v2.0 | PESTLE & SWOT completed. Pre-war baseline + Iran emergency review. | 1.02
4.2 | Understanding needs and expectations of workers and other interested parties | F6 | Completed | SM/HSE/REG/001 v1.0 | 21 parties mapped. Power/Interest Matrix. Iran conflict flagged. | 1.03
4.3 | Determining the scope of the OH&S management system |  | Completed | SM/HSE/DOC/001 v1.0 | Scope statement defined and sent to Libero. | 1.01
4.4 | OH&S management system |  | Completed | SM/INT/DOC/001 Document Referencing Guide + SM/INT/REG/001 Document Register + management system folder structure (00-12). System architecture documented and operational. | Complete. System documented through referencing guide, register, and folder structure.
CLAUSE 5: LEADERSHIP AND WORKER PARTICIPATION
5.1 | Leadership and commitment |  | Completed | 17 signed policies across all disciplines. MR #1 conducted and minuted. CEO endorsement of campaign. Resource allocation for LMS, portals, certification, GCD role. Demonstrable active leadership. | Complete. Evidence through signed policies, Management Review, campaign endorsement, resource commitment.
5.2 | OH&S policy | F6, OFI7 | Completed | SM/HSE/POL/001 v1.0 | Policy with Cl. 5.2 mandatory commitments + VPSHR, conflict zones, weapons safety. | 1.04, 1.08
5.3 | Organisational roles, responsibilities and authorities |  | Completed | SM/INT/DOC/005 RACI Matrix v1.0 — 48 functions, 11 roles, 7 categories, dashboard with accountability summary | Complete. RACI matrix covers all management system functions. | 2.03
5.4 | Consultation and participation of workers |  | Completed | SM/INT/PRO/014 Worker Consultation and Participation Procedure v1.0 — consultation requirements, participation mechanisms, barriers removal, Safety App, BRAGs, debriefs | Complete. Procedure + existing mechanisms (Safety App, BRAGs, debriefs, change requests). | 2.04
CLAUSE 6: PLANNING
6.1.1 | Actions to address risks and opportunities — General | F2 | Completed | SM/HSE/PRO/001 Hazard ID & Risk Assessment Procedure v1.0 | Risk framework IS Finding #2 Procedure completed 31/03/2026. | 2.01
6.1.2 | Hazard identification and assessment of risks and opportunities | F2 | Completed | 9x RA-003 pattern RAs (SM/HSE/RA/002-010) + 10x BRAGs (SM/CAM/BRAG/001-010) + SM/HSE/MS/001 Method Statement: Test Fire at Sea (first MS in new Method Statement series) | All operational and office hazards assessed. 144 hazards across 9 RAs. Night ops gap identified via screening tool and filled. Test Fire at Sea (BRAG/010 + MS/001) added S39. BRAGs + method statements for frontline distribution. | 2.01, 2.17
6.1.3 | Determination of legal requirements and other requirements | F1 | Completed | SM/HSE/REG/002 Legal and Regulatory Requirements Register v1.0 SM/HSE/PRO/002 Legal and Regulatory Compliance Procedure v1.0 | Legal register (37 entries across 5 jurisdictions) + compliance evaluation procedure. ISO cross-references per entry. Compliance evaluation frequency set. Responsible person review before audit. | 1.05
6.1.4 | Planning action |  | Completed | Evidential — CWP, CMPs for audits, management review, risk assessment controls. System structure IS the evidence. | Complete. Plans documented across CWP, IA CMPs, RAs, and procedures. S34. | 2.01
6.2 | OH&S objectives and planning to achieve them |  | Completed | SM/INT/REG/006 - Company Objectives Register v1.0 (30 objectives, SMART, KPIs, RAG, dashboard) | Objectives and KPIs established 31/03/2026. Review History sheet provides Clause 9.1 monitoring evidence. | 2.02
CLAUSE 7: SUPPORT
7.1 | Resources |  | Completed | GCD role contracted. LMS built and live. Safety App live. Campaign portals live. 140+ documents produced. Libero engaged. Training courses deployed. Resource commitment evidenced through output. | Complete. Resource commitment demonstrated through deliverables and infrastructure.
7.2 | Competence | F2, OFI8 | Completed | SM/INT/PRO/012 Staff Training and Competence Procedure v1.0. SM/INT/REG/008 Training and Competence Matrix v1.0. LMS live with 21 courses. Competence framework operational. LMS rollout imminent. | Complete. Procedure + matrix + LMS all operational. Rollout in progress. | 3.01, 3.09
7.3 | Awareness | F3, F6, OFI7 | Completed | SM/INT/PRO/012 covers awareness requirements. LMS courses deliver awareness training (C01a-d induction/awareness, C09 incident reporting). Campaign portal + BRAGs (10) + method statements + bulletins for ongoing awareness. Campaign Launch Bulletin (SM/CAM/BUL/003) issued 16/04/2026 — portal live with 18-doc library + compliance tools. | Complete. Awareness delivered through LMS, campaign portal, BRAGs, and bulletbox talks. | 3.02-3.04
7.4 | Communication | F3 | Completed | SM/INT/PRO/016 Internal and External Communications Procedure v1.0. SM/INT/PRO/016-A/B Emergency Contact Posters (Athens, Lagos). Safety App emergency contacts page. Supersedes SOP-1003. | Complete. Procedure + office posters + digital contacts. S34 — 8 Apr 2026. | 1.07
7.5 | Documented information |  | Completed | SM/INT/PRO/002 Control of Documents v1.0. SM/INT/PRO/005 Control of Records v1.0 (needs XML fix but content complete). SM/INT/REG/001 Document Register v2.0. Full document control framework operational. | Complete. Document and records control procedures operational. PRO-005 XML fix pending. | 1.09
CLAUSE 8: OPERATION
8.1.1 | Operational planning and control — General |  | Completed | SOPs (SM/OPS/SOP/001 IOR, SM/OPS/SOP/002 WAF), risk assessments (RA-003 series 9 RAs, RA-004 series), BRAGs, procedures, training, Safety App. Operational planning and control evidenced through full management system. | Complete. Evidenced by the scale and integration of the management system.
8.1.2 | Eliminating hazards and reducing OH&S risks | F2, OFI6 | Completed | SM/HSE/PRO/001 Hazard ID and RA Procedure. SM/HSE/RA/002-010 (9 H&S RAs, 144 hazards). SM/SEC/PRO/001 Security RA Procedure. SM/CAM/BRAG/001-010. Controls framework operational. Periodic review scheduling to be established. | Complete. Hazard elimination and risk reduction framework operational. Review scheduling task created. | 2.01, 2.10
8.1.3 | Management of change | OFI1 | Completed | SM/INT/PRO/013 v1.0 | Full MoC procedure addresses 8.1.3 requirements | 1.06
8.1.4 | Procurement |  | Completed | SM/INT/PRO/017 Supplier, Contractor and Procurement Management v1.0 + SM/INT/FORM/004 (Supplier Approval Form) + SM/INT/FORM/005 (SCAR) + SM/INT/FORM/006 (Checklist) + SM/INT/REG/010 (Register) + SEV forms (SEC/FORM/003, 004) + SEV checklists (FORM/001 v1.1, FORM/002 v1.1) + PRO-004/005 v1.1 | Complete. Full procurement suite: procedure, Word forms, Excel checklists, register, SCAR. SEV docs corrected and unified. S34. | 2.09
8.2 | Emergency preparedness and response | F7 | Completed | SM/HSE/PRO/003 Emergency Preparedness and Response Procedure v1.0 — umbrella framework linking PRO-006, BCP, regional SOPs. IRT exercise planned before May 2026. | Procedure complete. IRT exercise (CWP 3.06) target: before end May 2026. | 2.05, 3.06
CLAUSE 9: PERFORMANCE EVALUATION
9.1 | Monitoring, measurement, analysis and evaluation |  | Completed | Evidential — NCR/CAPA register, dashboards on all registers, CWP tracking, Safety App incident data, training matrix, legal register, audit programme, management review minutes | Complete. M&M framework embedded across registers, dashboards, procedures, and operational tools. S34. | 2.16
9.2 | Internal audit |  | Completed | SM/INT/PRO/003 Internal Audit Procedure v1.0. SM-IA-26-001 (Document Control audit) + SM-IA-26-002 (Risk Management audit) completed. Audit programme operational with 10 months remaining in cycle. | Complete. Procedure + 2 audits conducted. Programme ongoing. | 2.15, 3.08
9.3 | Management review | OFI2 | Completed | SM/INT/PRO/019 Management Review Procedure v1.0 (11 input areas, 5 outputs) + SM-INT-MRM-001 v1.1 (data maturity note for implementation phase). MR #1 conducted. | Complete. Procedure rebuilt to 45001 spec, MRM-001 updated with implementation data maturity note. S34. | 2.14, 3.07
CLAUSE 10: IMPROVEMENT
10.1 | Incident, nonconformity and corrective action |  | Completed | Evidential — SM/INT/PRO/001 (NCR/CAPA), SM/INT/PRO/006 (Incident & Crisis), SM/INT/REG/004 (NCR Register), Safety App reporting, campaign awareness programme | Complete. NC/CA framework operational, incident management procedure live, reporting app live. S34. | 2.06
10.2 | Nonconformity and corrective action |  | Completed | SM/INT/PRO/001 NCR/OFI/CAPA Management v1.0 SM/INT/REG/004 NCR Register v1.0 (populated, dashboards, conditional formatting) SM/INT/FORM/001 Non-Conformance Report Form v1.0 Full lifecycle tracking operational since S12. | Complete suite: procedure + register + form. Fully operational. | 2.07
10.3 | Continual improvement |  | Completed | SM/INT/PRO/015 Continual Improvement Procedure v1.0 — sources of improvement, 4-tier prioritisation, leading/lagging indicators, Management Review input, records | Complete. CI framework operational. Feeds into existing NCR/CAPA register and Management Review. | 2.18, 4.07

## MS Transition
MANAGEMENT SYSTEM TRANSITION — CMP-003
Folder restructure, document referencing migration, and management system consolidation
Document Reference: | SM/INT/CMP/003 v1.0
Change Description: | Wholesale management system transition — new folder structure, document referencing system, consolidated ISO documentation
Change Owner: | Group Compliance Director
Effective Date: | 01 April 2026
Target Completion: | 30 June 2026
Ref | Task | Owner | Start Date | Target Date | Status | Notes
PHASE A: INFRASTRUCTURE
A.01 | Folder structure created (00-12 with sub-folders) | Compliance Director | 01/03/2026 | 07/03/2026 | Completed | Done in Session 5
A.02 | Document referencing system formalised (SM/INT/DOC/001) | Compliance Director | 07/03/2026 | 14/03/2026 | Completed | Done in Session 5
A.03 | Document register created (SM/INT/REG/001 v2.0) | Compliance Director | 14/03/2026 | 21/03/2026 | Completed | Done in Session 5
A.04 | Folder guide and quick-reference created | Compliance Director | 21/03/2026 | 28/03/2026 | Completed | Done in Session 5
PHASE B: DOCUMENT MIGRATION
B.01 | Existing policies migrated and re-referenced | Compliance Director | 01/04/2026 | 14/04/2026 | Completed | As policies are updated for 45001/Shell
B.02 | Existing procedures migrated and re-referenced | Compliance Director | 01/04/2026 | 21/04/2026 | Completed
B.03 | SOPs migrated — retain legacy refs until amended | Compliance Director | 01/04/2026 | 30/06/2026 | Completed | Shell amendments will trigger migration
B.04 | Risk assessments migrated | Compliance Director | 01/04/2026 | 14/04/2026 | Completed
B.05 | Forms library migrated | Compliance Director Compliance Administrator | 14/04/2026 | 30/04/2026 | In Progress | 12 TL operational forms rebuilt (SM/OPS/FORM/006-017). RUF forms already complete.
B.06 | Legacy reference mapping completed | Compliance Director | 01/04/2026 | 30/04/2026 | In Progress | Legacy Mapping sheet in register
PHASE C: RELEASE & COMMUNICATION
C.01 | Google Drive workspace set up | Compliance Director | 01/05/2026 | 07/05/2026 | In Progress | Post-Shell review
C.02 | Access permissions configured | Compliance Director | 07/05/2026 | 14/05/2026 | Pending
C.03 | Team briefing on new system | Compliance Director | 14/05/2026 | 21/05/2026 | Pending | All staff awareness
C.04 | Old system archived | Compliance Director | 01/06/2026 | 15/06/2026 | Pending
C.05 | Parallel running period complete | Compliance Director | 15/06/2026 | 30/06/2026 | Pending | Old system access removed